## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | CYRS
Ref Version |  | V1.2
Auther |  | Tarek Sharaby
Last update |  | 24/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V0.2 | CYRS | Page 1 | Status of document must be changed from Draft to Proposed and then Releases after accomplishing cross review on it. | Accepted | Open
29/01/2020 | A.Ali | V0.2 | CYRS | All pages | Redundancy in Version field besides Date in header table. | Accepted | Open
29/01/2020 | A.Ali | V0.2 | CYRS | Contents | Update Table of Content numbering specially for Functional Requirements section. | Accepted | Open |  | Accepted
29/01/2020 | A.Ali | V0.2 | CYRS | All | There is no Reference table for the reference document , even CYRS should have one and the reference is the customer Requirement for the product | Accepted | Open |  | Refused
29/01/2020 | A.Ali | V0.2 | CYRS | Functional Requirements | You need to make your requirement more clarified from the system level prospective. In REQ_PO2EBL_CYRS_02_V02 instead of saying when the switch is pressed again, the blender shall operate on the higher speed level until it reaches the maximum level, and the next press shall turn it off. You can say: the blender shall operate between 3 different speeds (Speed1 → Speed 2 → Speed 3) triggered by a button press after the fourth press it returns back to its initial state (off). | Accepted | Open
29/01/2020 | A.Ali | V0.2 | CYRS | All | REQ_PO2EBL_CYRS_03_V02 : You can list all HW Req in hardware software interface document (HSI) , because in this requirement nothing related to HW as it more likely SW, so you need to update its #Imp to be only SW and if you see that you need a HW requirement defined this part of system, you could add it in HSI. | Accepted | Open
29/01/2020 | A.Ali | V0.2 | CYRS | All | REQ_PO2EBL_CYRS_04_V02: There isn’t a customer specification states that you need to turn on a corresponding led according to changing in speed levels. You shouldn’t take a step forward and guess something not mentioned by the customer in CRS until taking customer approval. | Accepted | Open |  | Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open