## Introduction
Project Name |  |  | Electric Blender
Ref Document |  | CYRS
Ref Version |  | V2.1
Auther |  | Abdelrahman Ali
Last update |  | 2020-10-02
History
Version | Auther |  | Date | Change
0.1 | A.Ali |  | 29/01/2020 | Initial creation
0.2 | A.Ali |  | 2020-07-02 | Update review sheet & close old points
0.3 | A.Ali |  | 2020-10-02 | Update review sheet & close old points

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V0.2 | CYRS | Page 1 | Status of document must be changed from Draft to Proposed and then Releases after accomplishing cross review on it. | Accepted | Resolved
29/01/2020 | A.Ali | V0.2 | CYRS | All pages | Redundancy in Version field besides Date in header table. | Accepted | Resolved
29/01/2020 | A.Ali | V0.2 | CYRS | Contents | Update Table of Content numbering specially for Functional Requirements section. | Accepted | Resolved |  | Accepted
29/01/2020 | A.Ali | V0.2 | CYRS | All | There is no Reference table for the reference document , even CYRS should have one and the reference is the customer Requirement for the product | Accepted | Resolved |  | Refused
29/01/2020 | A.Ali | V0.2 | CYRS | Functional Requirements | You need to make your requirement more clarified from the system level prospective. In REQ_PO2EBL_CYRS_02_V02 instead of saying when the switch is pressed again, the blender shall operate on the higher speed level until it reaches the maximum level, and the next press shall turn it off. You can say: the blender shall operate between 3 different speeds (Speed1 → Speed 2 → Speed 3) triggered by a button press after the fourth press it returns back to its initial state (off). | Accepted | Resolved | AAL 7/2/2020 : This point will be still open until remove from Imp#HW as we discussed that any requirements related to HW must be described and clarified well from HW prospective inside HSI document.
29/01/2020 | A.Ali | V0.2 | CYRS | All | REQ_PO2EBL_CYRS_03_V02 : You can list all HW Req in hardware software interface document (HSI) , because in this requirement nothing related to HW as it more likely SW, so you need to update its #Imp to be only SW and if you see that you need a HW requirement defined this part of system, you could add it in HSI. | Accepted | Resolved |  | Open
29/01/2020 | A.Ali | V0.2 | CYRS | All | REQ_PO2EBL_CYRS_04_V02: There isn’t a customer specification states that you need to turn on a corresponding led according to changing in speed levels. You shouldn’t take a step forward and guess something not mentioned by the customer in CRS until taking customer approval. | Accepted | Resolved |  | Resolved
2020-07-02 | A.Ali | V1.8 | CYRS | All | Version Date is different from the Date field in Release Table in page 2 , please apply a unique Date format for all date fields, add a title before the table in second page. |  | Open | AAL 10/2/2020 : there’s no title added before the table in second page.
2020-07-02 | A.Ali | V1.8 | CYRS | Page 6 | As discussed before Hardware Section shall be written in HSI document and instead of this section you can add a block diagram which describe how the system components interact with each others (I/Ps & O/Ps). |  | Open | AAL 10/2/2020: add a block diagram which describe how the system components interact with each others (I/Ps & O/Ps).
2020-07-02 | A.Ali | V1.8 | CYRS | Page 3 | In Revision table, the description column shall include the requirement IDs (modified/added or deleted) from CYRS document and a small description or brief about what changed in this requirement. |  | Resolved |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
2020-10-02 | A.Ali | V2.1 | CYRS | System Requirements | You need to add more requirements in CYRS which illustrate some features in your system Ex: you can add requirements which describe how to handle the communication between the inputs devices & o/p devices. |  | Open |  | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open