## Introduction
Project Name |  |  | Electric Blender
Ref Document |  | CYRS
Ref Version |  | V1.9
Auther |  | Abdelrahman Ali
Last update |  | 2020-10-02
History
Version | Auther |  | Date | Change
0.1 | A.Ali |  | 29/01/2020 | Initial creation
0.2 | A.Ali |  | 2020-07-02 | Update review points
0.3 | A.Ali |  | 2020-10-02 | Update review points

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V0.1 | HSI | Page 1 | Status of document must be changed from Draft to Proposed and then Released after accomplishing cross review on it. I expect if cross review was done by another team member , the status of document should be Released. | Accepted | Resolved
29/01/2020 | A.Ali | V0.1 | HSI | All pages | Redundancy in Version field besides Date in header table. | Accepted | Resolved |  | Accepted
29/01/2020 | A.Ali | V0.1 | HSI | All | There is no Reference table for the reference document , even HSI should have one and the reference is the customer Requirement for the product | Accepted | Resolved |  | Refused
29/01/2020 | A.Ali | V0.1 | HSI | Page 5 | System Block Diagram shall be updated to match customer specification defined in CRS , as there’s no mentioned specification states that there’s 3 LEDs and the arrow connected between push button and Microcontroller should be an input not output. | Accepted | Resolved
29/01/2020 | A.Ali | V0.1 | HSI | Page 6 | You could add a requirement ID to Pin Mode Representation section above the table , also there’s no block diagram added to the section 2.3 Speed Mode Block Diagram , if there’s no need for it , delete this section. | Accepted | Resolved
29/01/2020 | A.Ali | V0.1 | HSI | Page 7 | In Section 3 : Functional Requirements , you need to change the requirement ID for all the mentioned requirements and Implementation must be by HW as HSI document scope is only HW requirements. - Need to review HSI requirements again and add a related HW requirements from the system level prospective. | Accepted | Resolved |  | Open
2020-07-02 | A.Ali | V1.6 | HSI | All | Version Date format in header table is different from the Date field in Release Table in page 2 , plaese apply a unique Date format for all date fields , also HSI document stands for Hardware Software Interface. | Accepted | Open | AAL 10/2/2020 : Just change the abbreviation of HSI document as it’s stands for Hardware Software Interface. | Resolved
2020-07-02 | A.Ali | V1.6 | HSI | Page 6 | In Pin Mode Representation table, missed to add the sufficient pins to some components ex: Motor (has 2 DIO pins not one) , Also GND , VCC pins should be added as a used pins. | Accepted | Open
2020-07-02 | A.Ali | V1.6 | HSI | Page 7 | Redundant requirements between Functional Requirements and Pin Mode Representation table. As Functional requirements should describe a feature will be implemented in the system from the HW prospective , ask this question (What shall be considered when implement a HW for this feature?) . Ex: we you’ve a device or external peripheral works on 16 MHz clock and your selected Microcontroller has an internal oscillator 8 MHz , what you’ll need to consider in your HW implementation to overcome this issue. | Accepted | Open
2020-10-02 | A.Ali | V1.9 | HSI | All | You need to check the functional requirements section again as all what is written inside this section doesn’t related to HW requirements. |  | Open |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open