## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | CYRS
Ref Version |  | V1.2
Auther |  | Tarek Sharaby
Last update |  | 24/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V0.1 | HSI | Page 1 | Status of document must be changed from Draft to Proposed and then Released after accomplishing cross review on it. I expect if cross review was done by another team member , the status of document should be Released. |  | Open
29/01/2020 | A.Ali | V0.1 | HSI | All pages | Redundancy in Version field besides Date in header table. |  | Open
29/01/2020 | A.Ali | V0.1 | HSI | All | There is no Reference table for the reference document , even HSI should have one and the reference is the customer Requirement for the product |  | Open |  | Refused
29/01/2020 | A.Ali | V0.1 | HSI | Page 5 | System Block Diagram shall be updated to match customer specification defined in CRS , as there’s no mentioned specification states that there’s 3 LEDs and the arrow connected between push button and Microcontroller should be an input not output. |  | Open
29/01/2020 | A.Ali | V0.1 | HSI | Page 6 | You could add a requirement ID to Pin Mode Representation section above the table , also there’s no block diagram added to the section 2.3 Speed Mode Block Diagram , if there’s no need for it , delete this section. |  | Open
29/01/2020 | A.Ali | V0.1 | HSI | Page 7 | In Section 3 : Functional Requirements , you need to change the requirement ID for all the mentioned requirements and Implementation must be by HW as HSI document scope is only HW requirements. - Need to review HSI requirements again and add a related HW requirements from the system level prospective. |  | Open |  | Open
Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open