## ProjectPlan
2020-01-21
Daily
|  |  | 1 |  |  |  |  | 1899-12-31
1 Jan '00
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Phase 1: Initiation |  |  | 2020-01-21 | 2020-01-24 | 2020-01-21
Week 1
CYRS |  | Ibrahim, Farag | 2020-01-22 | 2020-01-23 | 2020-01-22 | 2020-01-23
SRS |  | Kariman | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-01-24
HSI |  | Amira, Ali | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-01-24
SIQ |  | Ali | 2020-01-23 | 2020-01-23 | 2020-01-22 | 2020-01-23
RTM |  | May | 2020-02-06 | 2020-02-07 | 2020-02-06 | 2020-02-07
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Week 2
CYRS Resolve |  | Ibrahim | 2020-02-01 | 2020-02-02 | 2020-02-01 | 2020-02-06
SRS Resolve |  | Kariman | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-06
HSI Resolve |  | Amira | 2020-02-01 | 2020-02-03 | 2020-02-01 | 2020-02-06
CYRS Cross Review |  | Ali | 2020-02-03 | 2020-02-04 | 2020-02-04 | 2020-02-04
SRS Cross Review |  | Ibrahim | 2020-02-05 | 2020-02-05 | 2020-02-01 | 2020-02-06
HSI Cross Review |  | Farag | 2020-02-03 | 2020-02-04 | 2020-02-07 | 2020-02-07
Update RTM |  | May | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-07
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Week 3
CYRS Resolve | Solve issues described in point 9,10 and 11 in the review sheet | Ibrahim | 2020-02-08 | 2020-02-08 | 2/8//20 | 2/8//20
SRS Resolve | Solve issues described in point 7,8,9,10 in the review sheet | Kariman | 2020-02-08 | 2020-02-11 | 2020-02-08 | 2020-02-11
HSI Resolve | Solve issues described in point 1-6 in the review sheet | Amira | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08
CYRS Cross Review | Cross review on the CYRS | Ali | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08
SRS Cross Review | Cross review on the SRS | Farag | 2020-02-11 | 2020-02-11
HSI Cross Review | Cross review on the HSI | Ibrahim | 2020-02-08 | 2020-02-08 | 2020-02-08 | 2020-02-08
Week 3 Update
CYRS Resolve | Solve issues described in point 9,10 and 12 in the review sheet | Ibrahim | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-11
HSI Resolve | Solve issues described in point 8,9,10,11 in the review sheet | Amira | 2020-02-12 | 2020-02-13 | 2020-02-12 | 2020-02-13
CYRS Cross Review |  | May | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-11
Week 3 Update 2
CYRS Resolve | Solve issues regarding missing requirements | Ibrahim | 2020-02-19 | 2020-02-20 | 2020-02-19 | 2020-02-20
SRS Resolve | Breaking down requirements into more atomic requirements | Kariman | 2020-02-19 | 2020-02-20 | 2020-02-19 | 2020-02-20
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Week 4
CYRS Update | Updating CYRS's requirement 2 and 5 and defining system constraints | Ibrahim | 2020-02-21 | 2020-02-22 | 2020-02-21 | 2020-02-22
SRS Update | Updating SRS requirements to reflect the system constraints defined in CYRS | Kariman | 2020-02-22 | 2020-02-23 | 2020-02-22 | 2020-02-23
HSI Update | Updating HSI requirements to reflect the system constraints defined in CYRS | Amira | 2020-02-22 | 2020-02-23 | 2020-02-27 | 2020-02-28
GDD | Initial creation of GDD document | Ali, Farag | 2020-02-23 | 2020-02-26
GDD Review |  | May | 2020-02-26 | 2020-02-27
CYRS Cross Review |  | May | 2020-02-22 | 2020-02-22 | 2020-02-22 | 2020-02-22
SRS Cross Review |  | Amira | 2020-02-23 | 2020-02-23
HSI Cross Review |  | Ibrahim | 2020-02-23 | 2020-02-23
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Week 5
GDD Document | Software Context, Software Features | Ali | 2020-02-29 | 2020-03-01
GDD Document | Adding requirements table and APIs | May | 2020-02-28 | 2020-02-29 | 2020-02-28 | 2020-02-29
GDD Document | Updating layered Architecture (Update) , Input and ouptut signals | Farag | 2020-03-01 | 2020-03-02
GDD Cross-Review |  | Amira | 2020-03-02 | 2020-03-02
Switch CDD |  | May, Ibrahim | 2020-03-03 | 2020-03-05
Switch CDD Cross Review |  | Kariman | 2020-03-03 | 2020-03-05
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Week 6
GDD Document Update | Updating GDD document considering the review points | May, Ibrahem | 2020-06-03 | 2020-09-03 | 2020-06-03 | 2020-09-03
CDD Document Update | Updating CDD document considering the review points | May, Ibrahem | 2020-06-03 | 2020-09-03 | 2020-06-03 | 2020-09-03
GDD Cross-Review |  | Amira | 2020-09-03 | 2020-10-03
CDD Cross Review |  | Kariman | 2020-09-03 | 2020-10-03
RTM Update |  | May | 2020-11-03 | 2020-12-03
Phase 2: Implementation
TASK DESCRIPTION | Task Description | ASSIGNED TO | PLAN START | PLAN END | ACTUAL START | ACTUAL END | Notes
Dimension Calculations |  | Ibrahim | 2020-03-10 | 2020-03-11
Outer body design | Desigining the Blender Body on solid works | Farag | 2020-03-10 | 2020-03-15

## Help
HELP
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
About
This project planner template was designed to provide a simple way to create a project schedule with a Gantt chart that shows both planned and actual dates. Other than that, it contains very few features, which may be great if you want something simple.
Want more features?
Learn About Gantt Chart Template Pro
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Text Within the Gantt Chart
You can enter text within the gantt chart area, but that text does not move if you adjust the start/end dates or use the scroll bar.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can add columns to the right of the Gantt chart by copying and pasting entire columns.
Conditional Formatting
The bars of the Gantt chart are created using conditional formatting. This spreadsheet is not designed to allow you to change the colors for different bars. Use Gantt Chart Pro if you want to do that.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Other Templates
Visit Vertex42.com to find other project management templates.
Project Management Templates

## ©
Project Planner Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.