## ProjectPlan
ELECTRIC BLENDER | [59 empty] | [42]
KENOVO
GROUP A
Project Leader: May Alaa El-din |  |  |  |  | Project Start: | 2020-01-21
[5 empty] | Display: | Daily
[5 empty] | Display Period: | 1 | time axis 2020-01-21 to 2020-03-15
Software Project Plan | [11 empty] | 21 Jan '20 | 22 Jan '20 | 23 Jan '20 | 24 Jan '20 | 25 Jan '20 | 26 Jan '20 | 27 Jan '20 | 28 Jan '20 | 29 Jan '20 | 30 Jan '20 | 31 Jan '20 | 1 Feb '20 | 2 Feb '20 | 3 Feb '20 | 4 Feb '20 | 5 Feb '20 | 6 Feb '20 | 7 Feb '20 | 8 Feb '20 | 9 Feb '20 | 10 Feb '20 | 11 Feb '20 | 12 Feb '20 | 13 Feb '20 | 14 Feb '20 | 15 Feb '20 | 16 Feb '20 | 17 Feb '20 | 18 Feb '20 | 19 Feb '20 | 20 Feb '20 | 21 Feb '20 | 22 Feb '20 | 23 Feb '20 | 24 Feb '20 | 25 Feb '20 | 26 Feb '20 | 27 Feb '20 | 28 Feb '20 | 29 Feb '20 | 1 Mar '20 | 2 Mar '20 | 3 Mar '20 | 4 Mar '20 | 5 Mar '20 | 6 Mar '20 | 7 Mar '20 | 8 Mar '20 | 9 Mar '20 | 10 Mar '20 | 11 Mar '20 | 12 Mar '20 | 13 Mar '20 | 14 Mar '20 | 15 Mar '20
WBS | TASK DESCRIPTION | Task Description | ASSIGNED TO | Type | PROGRESS | PLAN START | PLAN END | ACTUAL START | ACTUAL END | ACTUAL DAYS | Notes | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
| Phase 1: Initiation |  |  |  |  | 2020-01-21 | 2020-01-24 | 2020-01-21
Week 1
| CYRS |  | Ibrahim, Farag | Non-Technical | 100% | 2020-01-22 | 2020-01-23 | 2020-01-22 | 2020-01-23
| SRS |  | Kariman | Non-Technical | 100% | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-01-24
| HSI |  | Amira, Ali | Non-Technical | 100% | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-01-24
| SIQ |  | Ali | Non-Technical | 100% | 2020-01-23 | 2020-01-23 | 2020-01-22 | 2020-01-23
| RTM |  | May | Non-Technical | 100% | 2020-02-06 | 2020-02-07 | 2020-02-06 | 2020-02-07
WBS | TASK DESCRIPTION | Task Description | ASSIGNED TO | Type | PROGRESS | PLAN START | PLAN END | ACTUAL START | ACTUAL END | ACTUAL DAYS | Notes | 43853 | 43854 | 43855 | 43856 | 43857 | 43858 | 43859 | 43860 | 43861 | 43862 | 43863 | 43864 | 43865 | 43866 | 43867 | 43868 | 43869 | 43870 | 43871 | 43872 | 43873 | 43874 | 43875 | 43876 | 43877 | 43878 | 43879 | 43880 | 43881 | 43882 | 43883 | 43884 | 43885 | 43886 | 43887 | 43888 | 43889 | 43890 | 43891 | 43892 | 43893 | 43894 | 43895 | 43896 | 43897 | 43898 | 43899 | 43900 | 43901 | 43902 | 43903 | 43904 | 43905 | 43906
Week 2
| CYRS Resolve |  | Ibrahim | Non-Technical | 100% | 2020-02-01 | 2020-02-02 | 2020-02-01 | 2020-02-06
| SRS Resolve |  | Kariman | Non-Technical | 100% | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-06
| HSI Resolve |  | Amira | Non-Technical | 100% | 2020-02-01 | 2020-02-03 | 2020-02-01 | 2020-02-06
| CYRS Cross Review |  | Ali | Non-Technical | 100% | 2020-02-03 | 2020-02-04 | 2020-02-04 | 2020-02-04
| SRS Cross Review |  | Ibrahim | Non-Technical | 100% | 2020-02-05 | 2020-02-05 | 2020-02-01 | 2020-02-06
| HSI Cross Review |  | Farag | Non-Technical | 100% | 2020-02-03 | 2020-02-04 | 2020-02-07 | 2020-02-07
| Update RTM |  | May | Non-Technical | 100% | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-07
WBS | TASK DESCRIPTION | Task Description | ASSIGNED TO | Type | PROGRESS | PLAN START | PLAN END | ACTUAL START | ACTUAL END | ACTUAL DAYS | Notes | 43864 | 43865 | 43866 | 43867 | 43868 | 43869 | 43870 | 43871 | 43872 | 43873 | 43874 | 43875 | 43876 | 43877 | 43878 | 43879 | 43880 | 43881 | 43882 | 43883 | 43884 | 43885 | 43886 | 43887 | 43888 | 43889 | 43890 | 43891 | 43892 | 43893 | 43894 | 43895 | 43896 | 43897 | 43898 | 43899 | 43900 | 43901 | 43902 | 43903 | 43904 | 43905 | 43906 | 43907 | 43908 | 43909 | 43910 | 43911 | 43912 | 43913 | 43914 | 43915 | 43916 | 43917
Week 3
| CYRS Resolve | Solve issues described in point 9,10 and 11 in the review sheet | Ibrahim | Non-Technical | 0% | 2020-02-08 | 2020-02-08
| SRS Resolve | Solve issues described in point 7,8,9,10 in the review sheet | Kariman | Non-Technical | 0% | 2020-02-08 | 2020-02-11
| HSI Resolve | Solve issues described in point 1-6 in the review sheet | Amira | Non-Technical | 0% | 2020-02-08 | 2020-02-08
| CYRS Cross Review | Cross review on the CYRS | Ali | Non-Technical | 0% | 2020-02-08 | 2020-02-08
| SRS Cross Review | Cross review on the SRS | Farag | Non-Technical | 0% | 2020-02-11 | 2020-02-11
| HSI Cross Review | Cross review on the HSI | Ibrahim | Non-Technical | 0% | 2020-02-08 | 2020-02-08
| Update RTM | Updating RTM to reflect modified requirements | May | Non-Technical | 0% | 2020-02-12 | 2020-02-12
Phase 1 Milestone
Phase 2 Title
Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Insert new rows ABOVE this one

## Help
HELP
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
About
This project planner template was designed to provide a simple way to create a project schedule with a Gantt chart that shows both planned and actual dates. Other than that, it contains very few features, which may be great if you want something simple.
Want more features?
Learn About Gantt Chart Template Pro
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Text Within the Gantt Chart
You can enter text within the gantt chart area, but that text does not move if you adjust the start/end dates or use the scroll bar.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can add columns to the right of the Gantt chart by copying and pasting entire columns.
Conditional Formatting
The bars of the Gantt chart are created using conditional formatting. This spreadsheet is not designed to allow you to change the colors for different bars. Use Gantt Chart Pro if you want to do that.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Other Templates
Visit Vertex42.com to find other project management templates.
Project Management Templates

## ©
Project Planner Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.